## Sheet1
S.No | Date | Time to report | Place of report | Tentative time of closing for the day | Village planned | Activity
1 | 2023-12-07 | 10:00 | Atmakur | 17:00 | Atmakur | Introduction: Will explain briefly about RDT, plan to visit tof Govt junior college Atmakur (Assistence to Govt buildings)
2 | 2023-12-08 | 10:00 | Atmakur | 18:00 | P.Yaleru | Women to women program, IFI, Holystic school visit, interaction with women Auto driver
3 | 2023-12-09 | 10:00 | Atmakur | 17:00 | Atmakur | Boys work shop, single mother income generation programme, raising nursery
4 | 2023-12-11 | 10:00 | Atmakur | 16:00 | Atmakur | 1.Breif introduction about DID sector 2.Interaction with Mandala vikalangula Samakhya leaders 3.Interaction with Self help group
5 | 2023-12-12 | 10:00 | Atmakur | 17:00 | Atmakur | Family welfare: nutrition distribution CBTs meeting
6 | 2023-12-13 | 10:00 | Atmakur | 18:00 | P.kothapalli, Atmakur | Women empowerment activities, sports center visit
7 | 2023-12-14 | 10:00 | Atmakur | 17:00 | Muttala | Income generation programmes for women, housing visit
8 | 2023-12-15 | 10:00 | Atmakur | 17:00 | Kalyandurg, Battuvanipalli | ortho workshop, sanitory napkins center, Digital and holystic school visit
9 | 2023-12-16 | 10:00 | Atmakur | 18:00 | Settur | Bicycle project, holystic school visit, RO water plant visit
10 | 2023-12-18 | 9:00 | Atmakur | 18:00 | Nijavalli, Jambugumpula | Ecology (special projects)
11 | 2023-12-19 | 10:00 | kalyandurg | 17:00 | kalyandurg | sponsorship orientation, councelling center visit
12 | 2023-12-20 | 10am | RDT field office | 17:00 | DK Thanda, Papampalli | ecology activities
13 | 2023-12-21 | 10:am | B.Yaleru | 18:00 | B.Yaleru | school visit, education records, water pipe line works
14 | 2023-12-22 | 10:AM | Atmakur | 17:00 | Y.Kothapalli | RDT houses visit, school building construction visit,
15 | 2023-12-23 | 9:00 | Atmakur | 17:00 | Kalyandurg | RDT Hospital visit, interaction with Regional Director
16 | 2023-12-26 | 10.00 AM | Atmakur | 14:00 | Atmakur | Review the visits and clarifications wherever necessary